Grantee / Project Title:

Grant ID:

Grant Year:

1) Goal Roll-Up (this reporting period)

Use the status definitions below. One line of evidence per Goal.

| Goal ID | Goal (verbatim from award) | Overall Status | One-line evidence (summarize what finished this period) |
| --- | --- | --- | --- |
| G1 | [text] | Completed / In Progress / Not Started / Not Required (Out-of-Period) | [e.g., O1.1–O1.3 met; GLP tox completed] |
| G2 | [text] |  |  |
| G3 | [text] |  |  |

Roll-up rules (apply consistently):

- Completed – All success criteria met exactly as stated.

- In Progress – Any in-period Objective is In Progress or Not Started (explain below).

- Not Required – No objective under a Goal is due this reporting period.

- Not Started – No in-period Objective is In Progress or Not Started (explain below).

2) Goal → Objective Alignment (detail)

List every Objective under the Goal, mark Period Scope, then set Status.

G1

Goal (verbatim): [paste text]

| Obj ID | Objective (verbatim) | Original Due | Current Status* | % Complete | Evidence (study #s, batches, sites, etc.) |
| --- | --- | --- | --- | --- | --- |
| O1.1 | [ ] | [mm/dd/yy] | Completed / In Progress / Not Started / Not Required (Out-of-Period) |  |  |
| O1.2 | [ ] | [ ] |  |  |  |
| O1.3 | [ ] | [ ] |  |  |  |

Progress Narratives (only for in-period Complete, In Progress or Not Started)

Create one block per affected Objective.

- Objective ID: [e.g., O1.2]

- Work completed this period (facts only):

  - [What was done; measurable outputs; e.g., “209 GMP bags manufactured; 2 sites SIV complete.”]

- Reason / root cause:

  - [Scientific, operational, vendor, seasonal, regulatory, staffing.]

- Recovery plan with owners & dates:

  - Action → Owner → Target date (mm/dd/yy)

- Revised timeline for this Objective:

  - Forecast finish: [mm/dd/yy] (original [mm/dd/yy])

Repeat the table + narrative for each in-period Goal only.